## Sheet1
Changes | Status on Local Server | Status on Staging Server | Delevary Date | Feedback | Developer
On posting a project, it should read “Post a Project” instead of “Post a Job” | Done | Done
“Name Your Job” should instead be “Name your project” | Done | Done
When we uploaded a file, it did not show – that may be what you were referring to, but it did not seem to work. | Done | Done | 31-05-2013
Submit should say “Post this project” | Done | Done
In MY CLIENTS, Send invoice should create a new invoice instead of repeating the current invoice. | Done | Done, Once Invoice send , Professional can not send the invoice again | 31-05-2013
In CONVERSATION, will it get to a point where the older conversations are on the next page – the latest message should be at the top | Done | Done | 31-05-2013
REFER is not used in the correct way and should be deleted from My Awarded Projects – referrals and projects are entirely separate things and do not relate to each other. | Working On | Working On | 2013-07-06
How do you create an invoice? | It is created , based on the amount to be paid . If you need any form or any spacial structure please let me know | It is created , based on the amount to be paid . If you need any form or any spacial structure please let me know |  | Yes - Creating invoices should be its own module. It is not related to the project module and is not created from projects.
My Awarded Projects should only show up in the PROJECTS tab/menu item – On that page, it should show My Awarded Projects and have a button to “Browse available projects” - it should not be in the Account homepage | Done | Done | 31-05-2013
Please switch My Od Hub Account to be after My Invoices | Done | Done | 31-05-2013
HOW REFERAL WORKS – There are two types of Referrals: Professional to Professional and Professional to Client PROFESSIONAL TO PROFESSIONAL REFERRAL – A professional gets another professional to sign up using their referral code or referral link (when you click the link, it takes you to a sign up page and uses the referral code of the referring professional). The Referring Professional receives a “soft credit” of X dollars, meaning that it shows up as a credit on their MY OD HUB account, but only can be used against new OD Hub fees (commissions, credit card fees, or anything else that OD Hub charges). This soft credit should default to $25, but the admin should be able to change the default and also change the credit amount for specific Professionals. PROFESSIONAL TO CLIENT – A professional gets a new client to sign up on OD Hub using the professional's referral code or referral link (when you click the link, it takes you to a sign up page and uses the referral code of the referring professional). The Client is then permanently linked to the professional, such that any services the client engages in will create a commission for the referring professional. The commission will default to 18% with 10% being credited to the Referring Professional's MY OD HUB account (only credit when payments happen) and 8% being credited to OD Hub Admin. The Admin should be able to change the defaults percentages for the site and for specific professionals. Any client that signs up without a referring professional still pays the default commissions but the full amount (default 18%) goes to OD HUB Admin. | Working On | Working On | 2013-07-06
Here is the list of filters. Also, in the admin, at one point it had a forum. Can we keep this for just the professionals? Additionally, have you had a chance to review the Paypal Adaptive Payments API. 1. Category (Leadership Coaching or Workshops) 2. Skill Set (See below) 3. Pricing (Hourly with ability to choose ranges or Maximum Contract Value with ability to set Minimum and Maximum) 4. Location Preference 5. Start Date (with ability to set range of dates or Start Immediately) Additionally, the skill sets on both this page and the Create a Job Proposal page should be as follows: FOR LEADERSHIP COACHING (label as Coaching Focus): General Management Accelerated Leadership Development/High Potential Career Job/Career Transition Conflict/Improving Relationships Executive Presence Derailment Prevention FOR WORKSHOPS...(Label as CREDENTIAL): Myers-Briggs Type Indicator (MBTI) Herrmann Brain Dominance Instrument (HBDI) DiSC Emotional Intelligence (EQ) Hogan 360 Feedback Assessment Centers Pre-employment Assessment Leadership On-boarding/Assimilation StrengthsFinder Strengths Deployment Inventory Team Building Strategy Sessions Keynote Speaking Change Management Management Consulting Other | Done | Done | 31-05-2013
When you click CONTACT, who would the email come from? How would you know when the Professional responded? | By clicking Contact, Recipient will be the Professional and sender will be logged client | By clicking Contact, Recipient will be the Professional and sender will be logged client
In the top bar, there is no need for the "REALISTIC PREVIEW" menu item. | Done | Done
Before the My Favorites, there should be Search Our Professionals and Post a Project buttons. | Done | Done
IN PROJECTS - it should have a Create a Project button | Done | Done
IN PROJECTS - where will attachments show up? If the proposal description is long, will there be a way to click to see the details of one proposal or will it all print on this page? | At present , file is attaching is working but needs to display. It will display in proposal section after login by client. This section is working on progress | At present , file is attaching is working but needs to display. It will display in proposal section after login by client. This section is working on progress | 31-05-2013
When you click AWARD - Project Awarded is misspelled - It should also give you menu items to return to your Client Homepage or Projects. What functionality does clicking AWARD have? Does it contact the Professional? How does it link the two? Can we edit what language would be shown after you click AWARD and what is email is sent to the professional? | Spelling is checked and done. After award the project , professional can found that under awarded project section and by clicking on project link. Page by clicking on project link is working on progress | Spelling is checked and done. After award the project , professional can found that under awarded project section and by clicking on project link. Page by clicking on project link is working on progress
ADDITIONS
Homepage - Testimonials button/link on bottom must work |  |  |  | Please Provide what are the functionality testimonial page should have
FOR OD Clients page must be developed |  |  | 2013-11-06 |  | Manish
FOR OD Professionals page must be developed |  |  | 2013-11-06 |  | Surajit
Use My Info from Linked In must work |  |  | 2013-10-06 |  | Surajit
Log in to od hub should say "Login to OD hub" |  |  | 2013-10-06 |  | Surajit
Login page should not ask for Client or Professional - should just know from credentials |  |  | 2013-10-06 |  | Manish
On login page, Sign Up button needs to be formatted/designed to match Login button |  |  | 2013-10-06 |  | Manish
In CLIENT - Profile buttons/functionality must work |  |  | 2013-10-06 |  | Surajit
Realistic Preview module must be testable |  |  | 14/6/2013 |  | Manish + Surajit
Create Your Job graphic needs to be changed to Create Your Project graphic |  |  |  | How that Graph should generate
Will there be a posting type (step 2 of posting a project)? If not, remove. |  |  | 2013-10-06 |  | Manish
In ClIENT - please move Post a Project and Search Professional to left side - put Search Professionals first and change it to Search Professionals |  |  | 2013-10-06 |  | Surajit
There are errors on Search Professionals page |  |  | 2013-10-06 |  | Manish
Invoice module must be ready for testing |  |  |  | Please provide how you want to establish the invoice feature. What are the field invoice feature should have
Referral link only allows you to refer other professionals? How do you refer clients to sign up? |  |  | 2013-07-06
Forum design needs to be closer to finished |  |  | 2013-12-06 |  | Manish
ADMIN
- Will all videos need to be in FLV format? |  |  | 14/6/2013
- Fees does not reflect our specifications |  |  | 2013-07-06
- What is the Topic link for? |  |  |  | Where is the topic ? What it should display
- When adding Testimonials, labels still need formatting - hard to read and does not fit design |  |  | 2013-10-06
- A minimal amount of functionality seems to be there in regards to client, professionals, and projects |  |  | 14/06/2013
CREATE CLIENT
- On submission, still does not log us in |  |  |  | Please give me the proper description , which submission you want to mean
Cannot edit email for When A client creates A profile, also want to be able to edit welcome message on the site |  |  |  | Email address cannot be changed as that is the primary email address and the User id of the site.
- No place to enter a REFERRAL CODE
CREATE PROFESSIONAL
- On submission, still does not log us in
Cannot edit email for When A client creates A profile, also want to be able to edit welcome message on the site |  |  |  | Email address cannot be changed as that is the primary email address and the User id of the site.
- No place to enter a REFERRAL CODE |  |  | 14/06/2013 | There is no place to enter Referral code , But refferral program will be work using refferral link
- The following has still not been addressed: |  |  | 14/06/2013
On creating a professional account, the Write about Credentials should be a large text box instead of one line. Can we also set all of the fields to be the same color (the off yellow color instead of navy). Select Services should be checkboxes instead of a drop down. Error occured on creating an account and same problem that it does not get you into your account, but simply gives you a thank you message. If we are going to require email validation for accounts, it should provide instruction in addition to the thank you message. |  |  | 14/06/2013
"How do you want to represent yourself to clients on Elance" should be on OD hub and delete the Individual/Company option |  |  | 2013-10-06
SIGN IN
- Wrong user name and password is not formatted well - can hardly see on blue background |  |  | 14/06/2013
CLIENT HOMEPAGE
- CONTACT functions properly, but needs design formatting - should better reflect the professional feel of our website and 'content' should instead be 'message' |  |  | 2013-10-06
- See Preview does not yet work |  |  | 14/06/2013
- PREVIEWS module not yet created |  |  | 14/06/2013
- PROFILE button does not take you to a page where you can edit your profile |  |  | 14/06/2013
PROFESSIONAL HOMEPAGE
- Please confirm that REFERRAL LINK will log the referral - no indication when you click the referral link - it would be nice if it showed a field of the name of the person that referred. |  |  | 14/06/2013
- D Hub Previews = # 45 should read 'OD Hub Previews = 45' |  |  | 14/06/2013
- PROFILE button does not take you to a page where you can edit your profile |  |  | 14/06/2013
PROJECT SEARCH PAGE - None of this previous feedback has been addressed
2. - When screen is not wide enough, side buttons block parts of the page
- WORKSHOPS should be "Workshops, Facilitation and Assessment" |  |  | 14/06/2013
- I assume "Skills" will update to the skills chosen when the project is posted
- On the individual projects, can we make the PROJECT NAME clickable just like the category is clickable? |  |  | 2013-10-06 | Please clear this point. Do you want to make project name clickable from project search page or only for individual project name will be clickable.
14/06/2013
PROJECT POST PAGE - None of the following were addressed; additionally, CONTINUE does not do anything
- The Post Project button needs formatting - it does not match the rest of the buttons as far as design and font
- When I click on the WORKSHOPS filter , I do not get the Workshops filter options, which are different than coaches - I would think you may have to choose one or the other first before displaying any filter options since clicking Coaches should display one set of filters and clicking Workshops should display a different set. |  |  | 2013-10-06
- Missing links in the footer |  |  |  | Please provide what are the links are missing in footer
BIDDING MODULE - What happened to this module
- Share does not work |  |  |  | How share link should work? Will that project link will shared with reffered professional. If it is , then will reffered user get an email for that. Please describe
- Nothing happens on CONTINUE |  |  |  | By clicking on Continue button, I can able to post my proposal. It's working from my end. Please describe using a screen shot